## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Koduru Nandini | 2024-11-27 | Error in model accuracy using Whisper; replaced with Web Speech API. | Sprint 1 | Koduru Nandini | Functionality | Integrated Web Speech API to improve accuracy and resolved errors. | 2024-11-25 | Closed | API performs accurately without errors.
2 | Koduru Nandini | 2024-12-11 | Integrity issue: Data not being added to the cloud database using MySQL. | Sprint 2 | Koduru Nandini | Database | Switched to PostgreSQL for seamless cloud integration. | 2024-12-06 | Closed | Resolved with PostgreSQL integration.
3 | Koduru Nandini | 2024-12-15 | Delay in real-time processing for multilingual input. | Sprint 3 | Koduru Nandini | Performance | Optimized backend logic to reduce processing time. | 2024-12-12 | Closed | Improved response time significantly.
4 | Koduru Nandini | 2024-12-18 | Speech recognition fails intermittently in noisy environments. | Sprint 4 | Koduru Nandini | Functionality | Added noise cancellation preprocessing to improve input clarity. | 2024-12-16 | Closed | Noise handling is effective; performance improved.
5 | Koduru Nandini | 2024-12-25 | Frontend mic icon does not respond on some mobile browsers. | Sprint 5 | Koduru Nandini | UI/UX | Tested and fixed compatibility issues for different mobile browsers. | 2024-12-23 | Closed | Tested on all major mobile browsers; issue resolved.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others